## README
StartupHub — Research Database (Phase 0)
Positioning · Landscape Sweep · Competitive Deep Dive ¦ Compiled 18 October 2026
FIELD | VALUE
Project | StartupHub
Phase | Phase 0 — Positioning, Landscape Sweep & Competitive Deep Dive
Status | Complete (initial pass)
Compiled / Access date | 2026-10-18
Geography | India
Sources registered | 76 (44 government primary + 32 competitive)
Competitors profiled | 15
Pricing records | 52
Positioning gaps | 13 (3 CRITICAL, 4 HIGH, 6 MEDIUM)
Open questions | 18 (3 BLOCKING)
Decisions logged | 12
Problem areas | 12 (7 DOCUMENTARY, 4 INFERRED, 1 ASSUMED)
THE FIVE FINDINGS THAT CHANGE THE PROJECT
1. India digitised innovation ACCOUNTABILITY, not innovation OPERATIONS. Every mandated system is a compliance ledger keyed on events and snapshots; none is a system of record keyed on a venture over time.
2. The IIC portal has a menu item 'IPR/TTO Centres' that registers a TTO's existence and floor area — and has NO field anywhere to record a single patent. Zero of 11 direct competitors have an IPR module. National HEI patent filings grew 119% in two years.
3. The market is NOT empty. NestLens Orbit publishes INR 75,000/yr all-in. todo.md's assumed Rs 1.2L sits ABOVE the cheapest credible Indian incumbent.
4. Three capabilities have zero competitors across 11 vendors: IPR lifecycle, TRL as a first-class object, and YUKTI-NIR/IIC/ARIIA export. All three are MANDATED by India today. This is a mandate-shaped hole, not a feature gap.
5. The real competitor is free, and it is WhatsApp. IISc's own IIC page links students to a WhatsApp group. Notion/Airtable/Coda at IIC scale cost Rs 26k-1.73L — inside our band — and all three gate audit logs behind Enterprise with no retroactive history.
⚠️ THREE BLOCKING UNKNOWNS — NOTHING HERE IS TAM-READY
OQ-01 The current official IIC count is UNVERIFIED. Last official PIB figure: >6,400 (Nov 2022) — four years stale. This is the closest proxy for our denominator.
OQ-02 AICTE / engineering-college counts are UNVERIFIED. AICTE's dashboard returned HTTP 404 during research.
OQ-03 Willingness to pay is completely unvalidated. We have competitor ASKING prices, not what an institution would PAY.
Every figure in this workbook carries a source, an as-of date, and a reliability grade. Rows flagged CONFLICT must never be collapsed into a single number.
EVIDENCE TIER STANDARD
Tier | Meaning
TIER 1 | Primary — government publications, official statistics, official pricing pages, statutes, our own interviews/pilot data
TIER 2 | High-quality secondary — IIM/IIIT research, established consulting, World Bank/OECD, peer-reviewed
TIER 3 | Market intelligence — Tracxn, Crunchbase, Factly/Dataful, SaaS directories (G2, Capterra, GetApp)
TIER 4 | Community — vendor blogs, LinkedIn, Reddit, YouTube, review-site excerpts
VERIFIED | read directly from a primary source
LISTED | third-party directory, not the vendor
NOT_PUBLIC | gated behind login or sales call
UNVERIFIED | could not be confirmed; do not cite externally

## Open_Questions
Open Questions — 18, of which 3 are blocking
Nothing here is silently resolved. If sources disagree, both go in this sheet.
id | priority | area | title | what_we_know | why_it_blocks | what_would_settle_it | interim_handling | source_ids | status
OQ-01 | BLOCKING | Market | The current official count of IICs is unverifiable | Last official PIB figure is 'more than 6,400' in Nov 2022 (GOV-006). MIC Brochure 2025 contains a national IIC count embedded as a vector graphic that did not survive PDF text extraction. A media claim of 'over 14,000 HEIs' (Education Times, Feb 2025) is implausible against 6,400 and is not a verifiable attribution. | This is the single most important denominator in the project - the closest proxy for 'how many Indian institutions have a functioning innovation structure'. | Authenticated access to iic.mic.gov.in/institute-list; manual read of the MIC Brochure 2025 graphic; written query to MIC (mic-mhrd@gov.in); or an RTI. | Cite 6,400 with its 2022 date, never the current count. All market sizing must be shown both with and without IIC coverage. | GOV-006 | OPEN
OQ-02 | BLOCKING | Market | AICTE total approved institutions and the engineering-college-specific count | PRS compiled 8,489 technical institutions as of April 2026 (Tier 2). AICTE's Analytics Dashboard returned HTTP 404 and a search snippet showed '12,981 institutes' that could not be attributed to an academic year (filters spanned 2012-13 to 2026-27). Engineering-college-only count is unknown; AICTE publishes only bulk-login downloads. | Engineering colleges are a named segment in todo.md Phase 4. Sizing them requires the true count. | AICTE Centralized Support System login, or the annual approved-institution list. | Use 8,489 with a Tier-2 caveat. Never cite 12,981. | GOV-004 | OPEN
OQ-03 | BLOCKING | Pricing | Willingness to pay - completely unvalidated | We have competitor prices (Rs 75k-6.25L/yr) and free-tier anchors (Rs 0-1.73L/yr). We have ZERO primary evidence of what an institution would actually pay. todo.md carries an assumed Rs 1.2L/yr with no source - and it sits ABOVE the cheapest credible Indian incumbent. | Phases 7, 8, 16, 17 and 18 all depend on it. A financial model built on Rs 1.2L is currently an assertion, not a model. | Phase 3 interviews (10-15 institutions) using the VALUE framing - 'if this problem disappeared tomorrow, what would that save you?' - not 'would you pay Rs 1.2 lakh?'. Plus Phase 20 pilot conversion data. | Treat Rs 75,000 as a COMPETITIVE anchor, not a pricing decision. | COMP-001;COMP-004;COMP-008 | OPEN
OQ-04 | HIGH | Compliance | No public API anywhere in the mandated stack | No public API, developer documentation or bulk export endpoint found for IIC, YUKTI, NIRF, AISHE or MAARG (GOV-043). All are form-based web apps with per-activity manual uploads. data.gov.in carries some DPIIT/CSVs but they are parliamentary-answer snapshots, not live APIs; the Startup India SRF CSV returns 'Session Expired' on unauthenticated fetch. | If these systems have no APIs, integration is impossible and must be reimplemented as export-then-import. This changes the technical architecture (Phase 22) AND the pitch (one-click export, not live sync). | Written enquiry to MIC/MoE, or an RTI. | Assume NO API. Design export/import. | GOV-043 | OPEN
OQ-05 | HIGH | Market | Four rival datasets disagree on AIC count, three on TBI count | AIC: 83 (Lok Sabha Mar 2026) / 72 (AIM site) / 69 (AIM AIC page Jan 2024). TBI: 'more than 160' (DST) / '175+' (PIB Jan 2026) / 164 (ISTI). BioNEST: 74 (stats block) / 75 (table footer) on the SAME page. IIC: 6,400 (PIB 2022) / unreadable (MIC Brochure 2025) / '14,000' (media). | Presenting a single number without its source and date is how market sizing becomes indefensible. | See OQ-01 for the IIC figure. Others need MIC and DST written confirmation. | Never present a single number without source and date. Where a range matters, present the range. Use 83 for AIC. | GOV-006;GOV-008;GOV-010;GOV-011 | OPEN
OQ-06 | HIGH | Market | UGC and AISHE use different frames for 'university' | UGC (31.03.2024): 57 Central / 482 State Public / 478 State Private / 136 Deemed = 1,153. AISHE (2023-24): 55 / 462 / 464 / 125 = 1,289. | Mixing the frames produces a wrong total. Comparing them produces a false discrepancy. | Nothing - the frames are genuinely different, not one being wrong. This is permanent. | Keep the frames separate. Never cite '1,289 universities' without the year and frame. | GOV-002;GOV-003 | ACCEPTED - handled by rule
OQ-07 | MEDIUM | Market | Autonomous college count | Only 578/579 appears, on an AISHE dashboard whose vintage is unlabelled and whose college counts exceed the published 2023-24 totals. UGC publishes no authoritative total. UGC issued the UGC (Conferment of Autonomous Status upon Colleges) Regulations, 2023. | Autonomous colleges are a named segment in todo.md Phase 4. | UGC autonomous-college register or an RTI. | Use ~578 with a MEDIUM flag. | GOV-005 | OPEN
OQ-08 | HIGH | Market | Incubator/accelerator counts on Startup India are login-gated | BHASKAR's incubator and accelerator listings publish no aggregate count. The only public figure is a '600K strong' registry counter, which is NOT an incubator count and is marketing. Closest official national aggregate: MeitY Startup Hub 517+ incubators (Dec 2025, GOV-012). Per-state incubator counts are published by nobody. | todo.md Phase 5 asks for incubator and accelerator counts. They do not exist publicly. | Authenticated BHASKAR access, or a DPIIT RTI. | Use 517+ with the MeitY attribution and state the limitation. | GOV-012 | OPEN
OQ-09 | HIGH | Competition | Almost no independent review evidence exists in this market | Six of eleven direct competitors have ZERO third-party reviews. Gohorto: 3 GetApp, one vendor-referred. Founderhood: 1 G2 + 2 Capterra. AcceleratorApp: none found. incuTrack: 10 G2 (3.8), recent ones 'quite outdated'. Accubate: 26 Capterra (4.8) - the only real base. Consequence: nobody can prove a large Indian institution runs on their software. | todo.md Phase 11 (competitor user reviews) is THIN BY NECESSITY, not omission. Also: all G2/Capterra quotes come from search-index excerpts because both sites 403 automated fetch. | Direct re-verification of any quote before customer-facing use. Longer-term: one published StartupHub case study with named referees. | Treat all review quotes as Tier 4. Re-verify before external use. | COMP-006;COMP-009;COMP-010 | OPEN
OQ-10 | HIGH | Compliance | IIC's star-rating formula is not publicly documented | The official 'Rating and Scoring System' help page returns 'Coming Soon' (GOV-044). 3-star and 5-star ratings appear in institutional reports, so the system exists and works, but weights and thresholds are unknown. | FEATURE RISK. If StartupHub's core promise is 'your IIC data is already here, here's your star rating', we cannot build it without the formula. | MIC clarification, or reverse-engineering from institutional Performance Cards across many years. | Do not promise star-rating prediction in V1. | GOV-044 | OPEN
OQ-11 | HIGH | Market / Risk | BHASKAR overhaul - real threat or press noise? | DPIIT reportedly plans to turn BHASKAR into a 'National Startup Master Data' registry tracking the startup lifecycle; MeitY Startup Hub floated a similar tender (GOV-040, 21 May 2026, Moneycontrol). Tier 4 - trade press reporting a plan, not a notification. | If a national master data layer materialises, it becomes the upstream identity system and StartupHub must reconcile to it rather than duplicate it. | A published tender document or government notification. | Design for BHASKAR-ID reconciliation now. Do NOT cite externally until confirmed from a government source. Re-check before any launch. | GOV-039;GOV-040 | OPEN
OQ-12 | HIGH | Research gap | No peer-reviewed literature on Indian institutional reporting burden | Searched and NOT FOUND. What exists instead: ARIIA's own DCS statement that integration 'has reduced data submission efforts at the institute level by checking redundancy' (GOV-031); the AISHE 2023-24 report enumerating 12+ HEI-facing portals (GOV-006); RBI's SDMX paper as an analogy; NIRF methodology critiques that focus on ranking validity, not data-entry burden. | No one has quantified this burden. StartupHub should run its own primary time-and-motion study across ~20 IIC institutions. | Our own primary research - Phase 3 interviews plus a structured time-and-motion study. | A genuinely novel research opportunity. It is the difference between 'institutions have this problem' and '7 of 10 lose X hours per month to it'. | GOV-031 | OPEN
OQ-13 | HIGH | Procurement | Whether an institution-facing product can even be bought easily | Not yet researched. GeM procurement route (eligibility, registration, listing mechanics, security-questionnaire burden); DRE/Direct Purchase rules; data-localisation and on-premise requirements as procurement conditions; whether an IIC can sign a SaaS contract or needs the university as contracting party. | May be the hardest constraint in the business. EcoSync has already publicly conceded no SOC 2 / ISO 27001 and no uptime SLA - procurement is a real moat if StartupHub can clear it. | Phase 24 legal/compliance + Phase 19 GTM, plus talking to 2-3 institutional procurement officers. | Assume procurement is slow and evidence-heavy. Build the compliance output as an asset, not an afterthought. | COMP-003 | OPEN
OQ-14 | LOW | Market | The list of 31 States/UTs with a dedicated Startup Policy is login-gated | The count (31 of 36, as of 14 Sep 2026) is published; the list is not extractable. UP's Startup Policy 2026 was approved by State Cabinet on 6 July 2026, replacing the 2020 policy. Delhi, Gujarat, Tamil Nadu and UP institution-facing portals were NOT verified in this pass. | State policy coverage is a Phase 27 input and a Phase 19 partner-mapping input. | State government gazette archives; Startup India SRF participation records. | Cite the count, not the list. | GOV-015 | OPEN
OQ-15 | MEDIUM | Competition | University/technology-transfer software only partly researched | Elsevier Pure is well documented and priced (COMP-014) - minimum Indian deployment ~Rs 44.6L/yr + Rs 43.5L onboarding, roughly two orders of magnitude above StartupHub's band. But Invenio, Tech Transfer Ware, and the university innovation-management category were only lightly covered. A university CTO could argue 'we already own Pure'. | Innoloft's LoftOS case study (RWTH Aachen Collaeb) shows universities DO build and buy this category. | Phase 22 task: Invenio, Tech Transfer Ware, and the university TTO software category. | Note Pure as a procurement objection, not a feature competitor. | COMP-013;COMP-014 | OPEN
OQ-16 | MEDIUM | Product | Hindi / regional-language UI is claimed by almost nobody | Only Accubate lists Hindi as supported (on GetApp). Orbit's Sarvam-based Indian-language MOM transcription is the one genuinely India-specific AI feature found anywhere in the category. AcceleratorApp translates into seven European languages, Arabic and Ukrainian, but NOT Hindi. | If council meetings and mentor sessions happen in Malayalam/Tamil/Marathi, language could be a wedge or a non-issue. Nobody should guess. | Phase 3 interview question, not an assumption. | Ask in interviews. Do not build on it yet. | COMP-002;COMP-006 | OPEN
OQ-17 | MEDIUM | GTM | Campus ERP channel risk | Zero Indian campus ERP vendors have a genuine startup-incubation module (COMP-021), but several already claim 'NAAC SSR auto-generation, NIRF ranking data, AISHE submissions' (OnCampusERP, EduplusCampus). They compete for the compliance budget, own the institutional relationship, and hold the procurement precedent. Jaraka/Habbinson sells 'Institutional Excellence and IIC' as a module alongside its ERP. | A Phase 19 question: is StartupHub a partner, a competitor, or a module they'd resell? | Phase 19 GTM. Conversations with 2-3 ERP vendors. | Track them. Most likely a channel, not a competitor. | COMP-021 | OPEN
OQ-18 | LOW | Competition | Incu (Sweden) tracks patents as a data field | 'Moduler med nyckeldata om avtal, patent, kapital, varumarke' - 790 kr/user/month (~US$75) + EUR 3,500 implementation. The ONLY competitor found anywhere with any patent awareness. | If its patent module is deeper than a field, it partially invalidates GAP-01's 'zero competitors' framing. | A direct look at Incu's product and feature list. | GAP-01 stands unless Incu demonstrably has a patent WORKFLOW. | COMP-013 | OPEN

## Decision_Log
Decision Log — 12 decisions with their reversal conditions
Append-only. If a decision changes, add a new entry that supersedes it.
id | date | topic | decision | evidence | reverses_if | status
D-001 | 2026-10-18 | Process | Organise research by type of evidence, not by phase. | A claim gathered in Phase 9 and a claim gathered in Phase 20 must land in the same place if they prove the same thing. todo.md is already the phase map; duplicating it as the folder taxonomy creates two competing sources of truth that drift. | The 34 phases are later reordered such that phase number becomes the only meaningful retrieval key. | Active
D-002 | 2026-10-18 | Positioning | Do NOT freeze the beachhead customer in Phase 0. Examine all segments equally and in parallel. Narrowing happens at the end, from evidence. | todo.md Phase 0 asks for a frozen beachhead. But the segment census shows candidate segments differ by roughly three orders of magnitude - 1,289 universities vs 48,246 colleges vs 160+ DST TBIs. Choosing before competitor and margin evidence exists would be premature. User explicitly directed research in all directions first. | Evidence shows one segment is unserviceable (no budget, no data access, or fully pre-empted). | Active - intentionally diverges from todo.md Phase 0; deviation recorded so it is not mistaken for an oversight
D-003 | 2026-10-18 | Process | Run competitor research inside Phase 0, not at Phase 9. | todo.md itself states competitor research 'needs to be one of your highest-priority workstreams, not something we do at the end'. Confirmed empirically: LabelNest Orbit, IncubatX and EcoSync already sell institution-facing incubation software at Rs 75k-6L/yr with India-specific government-scheme coverage. A V1 scope frozen without knowing this would have been wrong on arrival. | Nothing - settled. | Settled
D-004 | 2026-10-18 | Positioning | The core structural finding: mandated systems are compliance ledgers, not systems of record. Anchor the positioning hypothesis on a category error in Indian innovation policy digitisation, not a missing feature inside an existing product. | Each mandated system has a different unit of record, none of them 'a venture, over time': IIC = the activity/event (16+/yr, each a form with 2 photos, a video URL, participant counts, one expenditure line); YUKTI = the innovation snapshot; NIRF = the spreadsheet row; AISHE = the institution-year aggregate; DPIIT = the recognition certificate. Sharpest proof: the IIC portal has a menu item called 'IPR/TTO Centres' that registers a TTO's existence and floor area - and has no field anywhere to record a single patent (GOV-022). Meanwhile NIRF demands patent commercialisation and income figures (GOV-028) and ARIIA demands patent application number and year (GOV-032), so institutions maintain a separate, off-platform patent ledger purely to answer two government screens. | A mandated system is found that does model ventures over time. MAARG comes closest (GOV-041) but is scoped to DPIIT-recognised startups, not institutional portfolios - re-verify before revisiting. | Active
D-005 | 2026-10-18 | Differentiation | Treat IPR lifecycle management, TRL-as-a-first-class-object, and YUKTI-NIR/IIC/ARIIA export as the strategic core of the differentiation hypothesis. | Across 11 direct competitors, not one has an IPR module. The only two traces in the entire market are a data field in a Swedish product (Incu) and a dashboard tile in IncubatX. Three government requirements make them unavoidable: YUKTI-NIR bands every submission by TRL and routes to different national programmes (GOV-023); ARIIA asks for 'Stage of Innovation (TRL Stage)' (GOV-032); MeitY's playbook mandates TRL benchmarking plus IP due diligence including freedom-to-operate and distinguishing ownership from a 2-year university tech-transfer licence (GOV-038). Every competitor tracks 'stage' as free text; nobody models TRL as a reportable, government-alignable object. | A competitor ships an IPR module. Given 6 of 11 vendors have zero third-party reviews and no named Indian institutional customers, low risk for ~12 months - but re-check before any external launch. | Active
D-006 | 2026-10-18 | Pricing | Treat LabelNest Orbit Launch at Rs 75,000/year all-in as the number that will appear in StartupHub's competitive deals. Keep Incubatee's Rs 3,95,200 year-one as the upper reference. Do NOT build the financial model on the Rs 1.2L assumption carried in todo.md. | COMP-001 (Orbit Launch Rs 75k / Starter Rs 99k / Growth Rs 1.25L / Scale Rs 2.5L) and COMP-004 (Incubatee Rs 3,95,200 year one). The Rs 50k-Rs 1.2L band in todo.md is anchored above the cheapest credible Indian incumbent. | Phase 8 pricing research or Phase 3 interviews establish a validated different price point. Until then Rs 75k is a COMPETITIVE anchor, not a pricing decision. | Active - CRITICAL CAVEAT: LabelNest publishes two conflicting Orbit price lists on its own domain (institutional tiers vs 'Orbit OS Rs 29,999/month'). In a procurement-comparison conversation where that surfaces, StartupHub wins on transparency.
D-007 | 2026-10-18 | GTM | Do not create a new budget line. Position against the IIC grant, the DST/NIDHI grant, or an Atal Incubation Centre allocation. | The decision-maker is typically a single nodal officer or IIC coordinator with no budget line of their own (COMP-024, COMP-025). India's compliance burden is already extreme - 'a typical firm has to navigate around 1,500 Acts which collectively impose 69,233 separate compliances and 6,618 independent filings' (COMP-028). A tool that reads as MORE compliance is dead on arrival; a tool that REDUCES re-keying into existing mandated portals has a strong pitch. Verified YUKTI-NIR innovations auto-pool into ARIIA Section 4 ranking (GOV-024), so a product that improves an institution's national ranking sells into a budget line that already exists. | Phase 19 GTM research finds a dedicated institutional innovation-software budget line at a material number of institutions. | Active
D-008 | 2026-10-18 | Pricing | Pricing floor stays above the free-tier anchors (Trello ~Rs 54k/yr at 10 users, Notion Plus ~Rs 86k/yr at 8 editors, ClickUp ~Rs 76k/yr). Differentiate on being the only thing that produces a compliant submission, not on cost. | COMP-017, COMP-020, COMP-001. The most dangerous pricing neighbourhood is Notion/Airtable/Coda at 8 editors - all inside or just below the Rs 50k-Rs 5L band - and all three gate audit logs behind Enterprise (COMP-017, COMP-019). Notion's audit log records events only 'starting from the time of upgrade', with NO retroactive history (COMP-031). Institutions need retroactive audit trails for accreditation and grant audits. That is a hard, citable, structural barrier. | Phase 8 reveals institutions genuinely cannot pay above Rs 50k/yr, in which case a deliberately thinner, cheaper product is required - but it would have to accept losing the audit-trail differentiator. | Active
D-009 | 2026-10-18 | Research method | Log negative research findings as findings. 'We searched and found nothing' is written into the record with the scope of the search. | Three negative findings materially change the work: no public API exists for IIC, YUKTI, NIRF, AISHE or MAARG (GOV-043); no Indian campus ERP vendor has a startup-incubation module (COMP-021); and no peer-reviewed literature quantifies Indian institutional reporting burden (OQ-12). Each removes a build-vs-buy option or opens a gap, and each would otherwise be re-researched every phase. | n/a | Active
D-010 | 2026-10-18 | Product | The biggest single sale blocker is migration, so migration must be a product. Guaranteed, free-or-subsidised migration - explicitly including WhatsApp group to structured records - is a Phase 20 pilot requirement and a Phase 22 build decision, not a customer service courtesy. | In Indian incubators the WhatsApp group IS the operational database (COMP-024 - IISc's own IIC links students to a WhatsApp group). Incu (Sweden) is the only vendor in the entire research stating it will import existing data at onboarding. Nobody has productised migration from open-question forms and spreadsheets. Migrating a university's data out of those is the #1 real blocker to any sale and is manual, unpaid work the BUYER would otherwise do. | Phase 12 feature-gap research finds a migration tool already commoditised. | Active
D-011 | 2026-10-18 | Risk | Watch item: BHASKAR may become the national master data layer. StartupHub's data model must be designed so it can reconcile to BHASKAR IDs rather than duplicate them. Do not build a proprietary startup identity. | DPIIT has reportedly planned an overhaul of BHASKAR into a 'National Startup Master Data' registry that would unify records and track the startup lifecycle, with MeitY Startup Hub floating a similar tender (GOV-040). CONFIDENCE: LOW - trade-press reporting of a plan, not a published notification. | No tender or notification materialises within ~18 months. Re-verify before any external communication; do not cite this externally until confirmed from a government source. | Active
D-012 | 2026-10-18 | Research method | Ignore hallucinated vendor claims; the market is full of them. Self-reported metrics, customer testimonials and award badges are Tier 4 unless independently corroborated. | Specific flags recorded: Gohorto's 'G2 High Performer 2026' badge rests on 3 reviews, one vendor-referred, with self-authored comparison pages rating itself 4.8 and every rival 2.1-3.6 (COMP-009); IncubatX's 'SOC 2-ready' is not SOC 2 (COMP-005); Incubatee claims no GST/TDS/UPI despite being an Indian vendor; and four names on the original watchlist (Applied, Bezu, Value Design Lab, Gobi) DO NOT EXIST as incubator software (COMP-016). Multiple vendors in this category serve AI-generated SEO content as their entire published feature set. | Independent verification becomes available for any specific claim. | Active