## Budget
The Revised Rs 6,00,000 Budget
PROVISIONAL. Every line is a planning estimate; no quotation has been obtained. The arithmetic reconciles - the build fails if it does not.
name | Q1 | Q2 | Q3 | Q4 | total | computed_total | share_of_envelope | note | evidence_status
Technology Development & Innovation Refinement | 90000 | 80000 | 75000 | 55000 | 300000 | 300000 | 50.0% | Core product, then ecosystem integration, then pilot hardening, then production readiness. | UNVERIFIED - no quotation obtained
Market Research & Pilot Study | 10000 | 15000 | 35000 | 40000 | 100000 | 100000 | 16.7% | Front-loaded cheaply, weighted to the pilot quarters, and heaviest in Q4 when willingness-to-pay has to be tested. | UNVERIFIED - no quotation obtained
IP Filing & Management | 10000 | 10000 | 5000 | 5000 | 30000 | 30000 | 5.0% | Check DPIIT facilitator benefits and statutory fee schedules before committing this line. | UNVERIFIED - no quotation obtained
Incubation & Mentorship | 15000 | 15000 | 15000 | 15000 | 60000 | 60000 | 10.0% | Flat across the year - the only line that does not flex. | UNVERIFIED - no quotation obtained
Startup Registration & Consultation | 0 | 10000 | 10000 | 5000 | 25000 | 25000 | 4.2% | Starts in Q2, once there is a product to register. | UNVERIFIED - no quotation obtained
Competitions / Exhibitions | 0 | 0 | 5000 | 5000 | 10000 | 10000 | 1.7% | Late-year, and travel only where explicitly eligible. | UNVERIFIED - no quotation obtained
Essential Contingency | 10000 | 20000 | 20000 | 25000 | 75000 | 75000 | 12.5% | A controlled reserve for essential unforeseen MVP/pilot requirements, subject to approval and funding rules. Not 'extra money'. | UNVERIFIED - no quotation obtained
TOTAL | 135000 | 150000 | 165000 | 150000 |  | 600000 | 100.0%

## Quarters
The One-Year Roadmap
Four quarters, four words, and a milestone at the end of each.
quarter | name | phase_word | objective | workstreams | workstream_items | outcome | slide_lines | slide_outcome | budget | evidence_status
Q1 | Foundation & MVP Definition | BUILD | Convert StartupHub from concept into a clearly defined, usable MVP. | Develop; Validation; Resources | Develop: Finalise core institutional problem and target users, Finalise MVP scope and user journeys, Startup onboarding and profile, Institution / incubator dashboard, Idea submission and management, Startup assessment, Basic incubation management, Basic mentor management, Basic IPR support workflow, Resource discovery, Basic analytics and reporting, User roles and access management ¦ Validation: User interviews, Institutional requirement mapping, Feature prioritisation, Initial usability testing ¦ Resources: Product development team, UI/UX support, Cloud/software services, Domain experts and institutional mentors | A functional MVP ready for controlled institutional testing. | Define MVP; Core workflows; Initial testing | MVP Ready | Rs 135,000 | UNVERIFIED - no quotation obtained
Q2 | Integrated MVP & Pilot Preparation | INTEGRATE | Connect the major ecosystem workflows and prepare the product for real users. | Develop; Validation; Resources | Develop: Mentor discovery and matching, Investor and funding discovery, IPR management workflows, Resource matching and requests, Market validation tools, Feedback and survey management, Milestone and roadmap tracking, Notifications, Document management, Improved dashboards, Basic AI-assisted recommendations ¦ Validation: Internal testing, User acceptance testing, Security and reliability checks, Feedback from initial institutions ¦ Resources: Development and product team, IPR/legal advisor, Mentors, Pilot institutions | An integrated product ready for pilot deployment. | Connect ecosystem; AI & matching; Pilot preparation | Pilot Ready | Rs 150,000 | UNVERIFIED - no quotation obtained
Q3 | Institutional Pilot & Product Refinement | PILOT | Put StartupHub into real institutional environments and measure actual usage. | Pilot; Refine; Market Validation | Pilot: Onboard selected institutions, Onboard startups, Configure institutional workflows, Run real startup-management activities, Collect user feedback, Track adoption and engagement, Measure time saved and process improvement ¦ Refine: Fix usability issues, Improve workflows, Improve recommendations, Improve dashboards and reporting, Strengthen security and reliability, Prioritise features based on real usage ¦ Market Validation: Institutional feedback, Customer interviews, Pricing validation, Willingness-to-pay assessment, Pilot-to-paid conversion assessment | Validated product with measurable pilot results and evidence of institutional demand. | Real institutions; User adoption; Feedback & refinement | Validated Product | Rs 165,000 | UNVERIFIED - no quotation obtained
Q4 | Launch Readiness & Early Commercialisation | LAUNCH | Convert the validated MVP into a market-ready product. | Complete; Commercial Validation; IP & Business | Complete: Final product refinement, Production deployment, Institutional onboarding process, Customer support process, Documentation and training material, Performance monitoring, Final analytics and reporting, Pricing and subscription structure, Sales and demonstration material ¦ Commercial Validation: Convert pilot institutions into paying customers, Establish institutional partnerships, Demonstrate product outcomes, Prepare expansion strategy ¦ IP & Business: Finalise relevant IP protection, Startup registration/compliance, Prepare investor and partnership documentation | Market-ready StartupHub with pilot evidence, initial institutional customers and a clear scale-up pathway. | Market readiness; Paying customers; Scale strategy | Market Ready | Rs 150,000 | UNVERIFIED - no quotation obtained

## Technology Budget
Inside The Rs 3,00,000 Technology Line
Half the entire envelope. Do not write invented vendor costs - obtain actual quotations and estimates.
quarter | label | amount | amount_display | share_of_tech | items | evidence_status
Q1 | Core build | 90000 | Rs 90,000 | 30.0% | Core product development; Product architecture and initial implementation; UI/UX; Basic cloud/software services | UNVERIFIED - no quotation obtained
Q2 | Ecosystem modules | 80000 | Rs 80,000 | 26.7% | Additional ecosystem modules; Integration of workflows; AI-assisted functionality; Cloud/software services | UNVERIFIED - no quotation obtained
Q3 | Pilot hardening | 75000 | Rs 75,000 | 25.0% | Pilot-specific improvements; Reliability and security improvements; User feedback implementation; Testing and deployment | UNVERIFIED - no quotation obtained
Q4 | Production | 55000 | Rs 55,000 | 18.3% | Production readiness; Final improvements; Deployment; Performance monitoring; Launch support | UNVERIFIED - no quotation obtained

## Funding Evidence
How We Prove Every Rupee
For every line, the artefact that would substantiate it. The obtained count is zero across the board, and that is the point.
category | budget_line | amount | amount_display | artefacts | n_artefacts | obtained | status | evidence_status
Technology | Technology Development & Innovation Refinement | 300000 | Rs 300,000 | Developer/team quotation; Software subscription quotations; Cloud/service estimates; AI/API pricing pages; Deployment/testing estimates | 5 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
Market Research | Market Research & Pilot Study | 100000 | Rs 100,000 | Interview plan; Survey costs; Pilot institution letters; Pilot onboarding requirements; User testing expenses | 5 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
IP | IP Filing & Management | 30000 | Rs 30,000 | IP consultant quotation; Government statutory fee schedule; Patent/trademark-related estimates | 3 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
Incubation | Incubation & Mentorship | 60000 | Rs 60,000 | Incubator quotation/invoice; Mentorship fee structure; Facility/service charges | 3 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
Registration | Startup Registration & Consultation | 25000 | Rs 25,000 | MCA/government fee schedule; Professional CA/CS/legal quotation | 2 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
Competitions / Exhibitions | Competitions / Exhibitions | 10000 | Rs 10,000 | Registration fee; Exhibition participation fee; Demonstration/material requirements; Travel only if explicitly eligible | 4 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained
Contingency | Essential Contingency | 75000 | Rs 75,000 | Controlled reserve for essential unforeseen MVP/pilot requirements, subject to approval and funding rules | 1 | 0 | NOT OBTAINED | UNVERIFIED - no quotation obtained

## Team
The Team For The Year
Six core roles we control, seven external dependencies we do not.
kind | role | detail | evidence_status
CORE TEAM | Product Lead | Product strategy, roadmap, requirements and stakeholder coordination | UNVERIFIED - no quotation obtained
CORE TEAM | Technology Team | Product development, integration and deployment | UNVERIFIED - no quotation obtained
CORE TEAM | Design Support | User experience and interface refinement | UNVERIFIED - no quotation obtained
CORE TEAM | Business/Market Lead | Institutional research, pilots and customer validation | UNVERIFIED - no quotation obtained
CORE TEAM | Domain Experts | IPR, incubation, startup ecosystem and institutional processes | UNVERIFIED - no quotation obtained
CORE TEAM | Mentors/Advisors | Product, business and market guidance | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Pilot institutions |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Incubation centre |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | IPR/legal professionals |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Cloud/software providers |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Institutional mentors |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Potential startup users |  | UNVERIFIED - no quotation obtained
EXTERNAL DEPENDENCY | Industry/institutional partners |  | UNVERIFIED - no quotation obtained

## Not Yet Verified
What Is Not Yet Verified, And What Would Settle It
This sheet is the reason the rest of the workbook is labelled provisional.
id | title | claim | checked | still_open
UV-01 | No rupee in this budget is evidenced | The full Rs 6,00,000 across 7 lines and 4 quarters. | Arithmetic. Every row total, every column total and the grand total were recomputed and agree. | Not one line has a quotation behind it. This is a planning estimate, and it must not be submitted as a costed proposal until the evidence register in 04_Funding_Evidence.md is filled.
UV-02 | The cited MIC document is a 2020 contest guide | That MIC's innovation framework 'expects a clear progression from idea/PoC toward prototype, with defined milestones, resources, mentoring and validation'. | The cited PDF was retrieved and read (20 pages). It is the IIC National Innovation Contest 2020 portal submission guide. It does document the idea -> PoC -> prototype progression, TRL banding, evaluation by the IIC with a score of 25 of 50 for approval, and mentoring of approved prototypes. | It is a contest guide for 2020, not the current general IIC handholding framework, and it does not state the 'cost, beneficiaries, impact and scalability' framing. That framing comes from a different MIC document which has not been identified or retrieved. Do not attribute it to this PDF.
UV-03 | Startup India IP-fee benefits are unconfirmed | That eligible DPIIT-recognised startups can access IP facilitators with the government bearing facilitator fees, and that patents receive an 80% filing-fee rebate. | The Startup India scheme page was retrieved. It renders its substantive content through JavaScript and the text could not be read, so the claim was not confirmed. | Confirm against the current DPIIT benefits page or the relevant gazette notification before relying on either benefit. This matters: it is the reason the IP line is only Rs 30,000 and should not grow without checking first.
UV-04 | MIC eligibility for Rs 6 lakh is not established | That Rs 6 lakh is the MIC-approved or eligible amount. | Nothing. This document makes no such claim and the folder states so explicitly. | The specific current call and guidelines applicable to the institution must be checked. The MIC material establishes an innovation-development and handholding framework, which is not by itself enough to infer eligibility for every proposed expense head.
UV-05 | Incorporation cost is not quantified here | That private-company incorporation carries statutory costs plus professional fees, varying by circumstance and state. | Stated as a variable, not a number. The folder asserts no amount. | The MCA and government fee schedules and the professional quotation will settle the Startup Registration line.
UV-06 | Market demand behind the roadmap is not evidenced | That institutions will buy, and at what price. | Nothing in this folder supports it. The pilot in Q3 and the willingness-to-pay assessment in Q4 are the activities that would test it. | Q3's pricing validation and willingness-to-pay assessment are the first point at which this claim becomes testable. Until then it is an assumption, and the Q3 and Q4 budgets should be understood as buying the test.